AGENDA

SUBJECT: 6TH & Main Streetscape - Auburn, Indiana

DATE/TIME: 	June 14, 2017 – 1:00 pm

LOCATION: Auburn City Hall

- Anticipated project schedule

  - Survey - Complete

  - 30% schematic design progress meeting – April 13

  - 60% design development progress meeting - May 11

  - 90% construction documents progress meeting – June 14

  - 100% construction documents submittal – July 14

  - Bidding Period – July 27, 2017 – August 24th, 2017

  - Major Construction start date - October 1, 2017

    - Fall 2017-Utilities/Spring 2018 – remainder of improvements

    - 6th & Main cannot be under construction for ACD Festival and Fair

    - ACD Festival August 30th – September 6th

    - Fair September 24th – September 30th

  - Substantial completion – June 30, 2018

- Construction Documents Drawings overview, page turn and specific design elements to discuss

  - 60% Plan Review Comments addressed.

  - Horizontal and Vertical Control Plan added

  - Demolition

  - Dimensional

    - ADA parking space added

    - Snow route and loading area signs removed to reduce amount of signage

    - Cricket’s access and dumpster

      - Two solutions have been identified

        - Solution 1: PNC bank allows access from the east drive and dumpster and transformer stay in current location

        - Solution 2: Cricket’s shares a dumpster with the 6th & Main business or the dumpster remains in its current location allowing a driveway to be installed. The transformer would stay within the right of way in a reduced landscape island. Preliminary discussions with the James group have taken place and they are open to this.

  - Grading

    - Sidewalk on Main Street – existing sidewalk cross slope exceeds 2% ADA maximum

      - Asphalt wedge has been increased to eliminate the 7” and 8” curb height

  - Utility plan & profile

    - 12” pipe extending eastward of the last structure with pipe plug is now shown on both the plan and profile views of C402.

  - Lighting and electrical

    - Underground Duct bank – coordinated with Auburn Electric

      - Catch basins along curb adjusted to the North to avoid duct bank conflict

  - Landscape plan

  - Site details

  - Coal Vault

    - Repair details provided

- Cost estimate overview

  - Base bid

  - Add alternates

    - Decorative plaques

    - Outlets at each tree location

    - Masonry Trash enclosures

    - West 6th Street Landscaping

    - Intersection Decorative Concrete

    - Low voltage – conduit and IT Box for future speakers

  - Deduct alternate

    - North Main Street

- Site furnishings and materials

  - Benches

Bike Racks

    - Provided by owner

  - Bollards

  - Lighting

    - Banner arms

    - 2 GFI outlets

    - Hanging flower baskets?

  - Sign Posts

  - Pavers

    - IL Campo Heritage Brown in Crosswalk

  - Trash Receptacle

  - Tree grates

  - Curbed concrete planters

  - Landscape material

  - Dumpster enclosures

    - Vinyl enclosure base bid

  - Decorative plaques

  - Decorative colored chevron pattern in intersection

- Next meeting-As needed to coordinate specific elements

/tmp/in/input.doc